**F. No. AB-11018/8/2024-Gen\_cord./E-27374**

**Government of India**

**Ministry of Fisheries, Animal Husbandry and Dairying**

**Department of Animal Husbandry and Dairying**

\*\*\*\*

**Krishi Bhawan, New Delhi**

**Dated: .11.2024**

**OFFICE MEMORANDUM**

**Subject: Monthly Report on the progress in implementation of  
important initiatives/flagship Programmes / Cabinet decisions of Department of Animal Husbandry and Dairying– reg.**

The undersigned is directed to enclose the Monthly report on the progress in implementation of Important Initiatives/Flagship Programmes/Cabinet Decisions of Department of Animal Husbandry and Dairying for the month of October, 2024 in the prescribed format enclosed at Annexure-I.

2. This issues with the approval of competent authority.

(S. Kamal Garg)

Under Secretary to the Government of India

Tel: 011-23382863

Email: [gargsk.edu@nic.in](mailto:gargsk.edu@nic.in)

To

The Director,

(Shri Naval Kishore Ram)

Prime Minister’s Office,

South Block, New Delhi.

**Annexure - I**

**Monthly Report on progress of implementation of Flagship Schemes of Department of Animal Husbandry and Dairying for the month of September, 2024**

**(1) Rashtriya Gokul Mission:**

1. **Objectives**
2. To enhance productivity of bovines and increasing milk production in a sustainable manner using advance technologies.
3. To propagate use of high genetic merit bulls for breeding purposes.
4. To enhance Artificial insemination coverage through strengthening breeding network and delivery of Artificial insemination services at farmers’ doorstep.
5. To promote indigenous cattle & buffalo rearing and conservation in a scientific and holistic manner.
6. **Achievements in terms of physical and financial progress**

**Financial Progress**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **(Rs in crore)** | | | | | | | | | | |
|  | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 |
| Allocation | 159.40 | 81.77 | 118.79 | 190 | 750.50 | 270 | 400 | 663 | 600 | 869.54 | 700 |
| Expenditure | 159.40 | 81.77 | 118.79 | 190 | 750.50 | 270 | 400 | 663 | 600 | 869.13 | 212.61 |

**Physical Progress**

1. Under Nation-wide artificial insemination programme, till now 10.17 crore Artificial Insemination have been performed and 7.30 crore farmers have been benefitted.
2. 43 IVF/ETT laboratories have been sanctioned and 22 laboratories are functional with production of 22549 viable embryos, 12586 embryo transfer and 1977 calves born.
3. Till now 30785 Multipurpose Artificial Insemination Technician in Rural India (MAITRIs) have been established.
4. **Efforts made for handholding/creating awareness**
5. Under the scheme, Farmers Training Programme, Fertility Camps, Workshops and Seminars etc. are organized and also, awareness generation through audio virtual aids, wall paintings/hoardings etc. are undertaken
6. Skill Development, training of professionals and existing Al workers
7. E-Gopala app & 1962 Farmers app launched for creating awareness among farmers.

**(2)** **National Programme for Dairy Development (NPDD) scheme**

**(I)** **Objective:** National Programme for Dairy Development (NPDD)” is implemented from 2021-22 to 2025-26 with the following two components: -

(a) The **Component 'A'** focuses towards creating/strengthening of infrastructure for quality milk testing equipment as well as primary chilling facilities for State Cooperative Dairy Federations/ District Cooperative Milk Producers’ Union/SHG run private dairy/Milk Producer Companies/Farmer Producer Organisations

(b) The **component ‘B’** of NPDD scheme “Dairying through Cooperative” aims to increase sale of milk and dairy products by increasing farmer’s access to organized market, upgrading dairy processing facilities and marketing infrastructure and enhancing the capacity of producer owned institutions thereby contributing to increase in return of milk producers in the project area.

**(II). Achievement in terms of physical and financial progress till 31.10.2024**

**Component A:**

**Financial:**

218 projects in 28 States and 2 Union Territory have been approved with the total cost of Rs. 3567.42 crore (Central Share Rs. 2644.43 crore) from 2014-15 to 2023-24 (31.10.2024). A total sum of Rs.2068.23 crore has been released for implementation of these projects against which Rs. 1709.93 crore has been utilized and Rs.283.99 crore is unspent upto 31.10.2024.

**Physical Achievements**

* 19,797 dairy cooperative societies formed/revived, 18.27 lakh new farmers were given benefit of membership of dairy co-operative societies and 107.98 lakh litre of additional milk procured under the projects.
* 25.52 lakh litres per day new milk processing capacity has been established.
* 4796 Bulk Milk Coolers with 110.91 lakh litres chilling capacity installed, 37233 Automatic Milk Collection Unit and Data Processing and Milk Collection Unit with Milk Analyser, 4267 Milk Analyser and 6184 Electronic Milk Adulteration Testing Equipment have been installed at village level dairy cooperative societies.
* 231 cooperative dairy plants at district/regional level (not having adulteration testing equipment) equipped for adulteration detection equipment with169 dairy plant laboratories have been equipped with FTIR Technology based milk analysers.
* About 17 State Level Laboratories are being establishment in 16 States.

**Component B:**

**Financial Progress**

In total 35 projects has been approved under the Dairying through Cooperatives (DTC)-NPDD Component B with a total project cost of Rs.1343.00 Cr having loan component of Rs 841.55 Cr, grant component of Rs.388.54 Cr. and Producer Institutions (PIs) share of Rs.112.92 Cr. Total grant of Rs.216.97 Cr and loan of Rs.195.06 Cr has been released to National Dairy Development Board for further disbursement to PIs for execution of approved project activities.

**Physical Progress**

Out of the total 35 projects, 12 projects have been approved in Bihar, 8 projects have been approved in Uttar Pradesh, 6 in Rajasthan, 2 in Andhra Pradesh, Punjab and West Bengal and 1 project each in Madhya Pradesh, Telangana, and Uttarakhand.

**As of Sep 2024, the following physical progress has been reported under component B of NPDD:**

* 1749 dairy cooperative societies formed/revived, about 51,079 farmers were given membership and 268.12 Thousand litres of additional milk procured under the projects.
* 25Visi coolers, 589 Deep Freezers and 3 Cold Store has been established under Marketing activities.
* 353 villages with 1922 animals for 86.7 MT feed have been undertaken for calf rearing program
* 885 villages with 21969 animals for 1242.65 MT feed have been undertaken for animal nutrition services
* 190 chaff cutter, 28 mowers, 26 low cost silage making units and 1 fodder storage godown has been created for fodder development.

**(III). Efforts made for handholding/ creating awareness about programmes/ process simplification etc.:**

Various stakeholders meeting both at regional & national level are conducted for creating awareness and sensitizing about the programme/scheme for better outreach.

**(IV). An analysis may be done and shared if desired progress is not taking place-**

**Component A:** Projects under NPDD scheme are capital intensive and approved for 2-4 years implementation period. Out of total 218 projects approved, 7 projects have been withdrawn by States,135 projects have been completed and remaining 76 projects are under implementation. As on 31.10.2024, 25.52 lakh litres per day new milk processing capacity has been established against the target of 28.65 lakh litres per day, 37233 Automatic Milk Collection Unit and Data Processing and Milk Collection Unit with Milk analyser installed against the target of 48505 at village level dairy cooperative societies, 4796 Bulk Milk Coolers with 110.91 lakh litres chilling capacity installed against the target of 6766 BMC with 165.92 Lakh litre. By considering the above facts, it may be mentioned that progress of the scheme is satisfactory.

**Component B:** Implementation of NPDD Component B started in 2022-23. The project worth 70% of the total budget has already been sanctioned by the Department. There are few more project proposals in pipeline. The financial targets as envisaged, is likely to be achieved in time.

**(V). The States with good performance and State with poor performance may also be mentioned (wherever applicable)**

Proposal under the scheme are received from State/UTs based on their requirement/demand. Therefore, bifurcation of good and bad performance may not be feasible. However, Department is regularly following up with the State for achieving the approved targets under the projects.

**(3) Dairy processing and Infrastructure Development Fund (DIDF):**

**(I) Objective of scheme/programme:**

Creation/ Modernisation of milk processing, value addition and chilling facilities.

**(II)** **Achievement in terms of physical and financial progress:**

**Progress/ Achievements:** 37 Projects from 12 States have been sanctioned by NDDB and NCDC. The financial and physical progresses are as under:

1. **Financial (as on 30.09.2024)**:
2. Total approved project outlay: Rs.6776.87 Crore
3. Loan sanctioned: Rs. 4575.22 Crore
4. Loan disbursed: Rs. 3426.04 Crore
5. Interest subvention released by GoI: Rs. 179.37 Crore (as on 31.10.2024)
6. **Physical (as on 31.08.2024)**:
7. Milk Processing Capacity established: 73.95 LLPD
8. Milk Chilling Capacity established: 3.40 LLPD
9. Drying Capacity established: 265 MTPD
10. VAP capacity established: 14.24 LLPD (milk equivalents)

**(III)** **Efforts made for handholding/ creating awareness about programmes/ process simplification etc.:**

Various stakeholder’s meetings were conducted both at regional and Central level for creating awareness & sensitization about the scheme for better outreach.

**(IV) An analysis may be done and shared if desired progress is not taking place:**

Under DIDF, as on 30.09.2024, Rs. 3624.04 Crore has been disbursed as loan for 37 projects with total outlay of Rs. 6776.87 Crore and loan share of Rs. 4575.22 Crore. Further, an amount of Rs. 179.37 Core (as on 31.10.2024) has been released to NABARD and NDDB as interest subvention.

**(V) The States with good performance and State with poor performance may also be mentioned (wherever applicable):**

Under DIDF, proposals from 12 States have been sanctioned and out of these 12 States, Karnataka has performed well, however, Kerala, Tamil Nadu and Madhya Pradesh could not show expected level of achievement.

**Action Plan:**DIDF has been restructured and integrated into the AHIDF as of February 1, 2024. Under this revised scheme, both cooperatives and private dairy plants are eligible to receive an interest subvention of 3% per annum. Additionally, cooperatives, similar to private entities, can now secure loans from any lending institution that qualifies under the scheme

**(4.) Supporting Dairy Cooperatives and Farmer Producer Organizations engaged in dairy activities (SDCFPO):**

**(I) Objective of scheme/programme:**

The objective of the scheme is to assist the Cooperative Societies and farmer producer organizations engaged in dairy activities by providing soft working capital loan to tide over the crisis on account of severely adverse market conditions or natural calamities. Due to Economic Impact of Covid-19 on Dairy Sector, Ministry of Fisheries, Animal Husbandry and Dairying has introduced a new component “interest subvention on Working capital loans for Dairy sector” as one of the component. Under this an interest subvention of 2% per annum on the working capital loan is being provided to the producer owned Institutes (POIs.). Further, for prompt and timely repayment, an additional 2% per annum interest subvention is payable at the end of the loan repayment/interest servicing period. Temporarily, the other component namely “working Capital loan” was kept in suspension since 2020-21.

**(II) Cumulative achievement in terms of physical and financial (As on 30.09.2024) :**

* **Total Sanction of Interest Subvention amount @ 2%: Rs. 688.89 crore**
* **Total working capital loan availed by Cooperatives/FPOs: Rs. 60,496.76 Cr.**
* **Total Cooperatives/Producers organizations assisted: 64 Nos.**
* **Total Interest Subvention amount released:  Rs. 563.88 cr. (Rs. 296.08 cr as regular interest subvention and Rs. 267.80 cr. as additional interest subvention amount).**

**(III)** **Efforts made for handholding / creating awareness about programmes/ process simplification etc.:**

Various stakeholders meetings were conducted and Administrative Approval for the scheme implementation have been issued by the Department. Wide publicity through pamphlets and social media were given.

**(IV) An analysis may be done and shared if desired progress is not taking place:**

SDCFPO is being implemented by NDDB. As reported by NDDB, there is huge demand for fund utilization under the scheme. 100% expenditure have been incurred under SDCFPO during the last couple of years, this implies that the scheme is operating satisfactorily.

**(V) The States with good performance and State with poor performance may also be mentioned (wherever applicable):**

Not applicable

**(5) Animal Husbandry Infrastructure Development Fund (AHIDF)**

**(I) Objective: Animal Husbandry Infrastructure Development Fund (AHIDF)** – is one of the Flagship schemes of Department of Animal Husbandry and Dairying launched under Prime minister’s AtmaNirbhar Bharat Abhiyan stimulus package on 24.06.2020 and has been realigned with merger of Dairy Processing Infrastructure Development Fund (DIDF) and has been extended for next three years with a fund size of Rs 29110.25 crore.

**(II)  Achievement in terms of physical and financial progress.**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category** | **Nos.** | **Processing Capacity** | **Direct Employment** |
| Dairy Processing and value addition | 173 | 209 LLPD | 15891 |
| Animal Feed Plant | 152 | 92.50 lakh MT per annum | 14556 |
| Meat Processing and value addition | 30 | 9.2 lakh MT per annum | 8500 |
| Breed Improvement Technology & Multiplication Farm | 112 | 8960 cows/buffaloes/pigs  147.35 crore poultry birds/chicks per Annum  91.44 cr. eggs per Annum | 8300 |
| Animal Waste to Wealth Management (Agri waste management) | 3 | 11000 MT/annum capacity of compressed gas | 43 |
| Veterinary Vaccine and Drugs Production Facilities | 3 | 90 lakhs No. Bolus, 400 lakh No. Tablets, 60,000 Kg powder, 70 lakhs vials and 2.74 L of liquid veterinary drugs and medicines per annum and 3 Crore Injectable Drugs per Year | 254 |

**Financial** - As on 1st November 2024, 879 projects with aggregate Project Cost of Rs.16962.60 cr. and term Loan of Rs. 11465.84 cr. have been marked eligible by the Department. 473 applications with aggregate Project Cost of INR 12243.60 cr. and Term Loan of INR 8266.03 cr. have been sanctioned by the banks. Till date, the Department has released interest subvention of Rs. 216.14 cr. for 298 projects.

**(III) Efforts made for handholding/creating awareness about programmes/ process simplification etc.**

The Department is organizing workshops / seminars / webinars for dissemination of scheme related information with lending institutions, entrepreneurs, industry associations etc. Also, the Department is in direct connect with various farmers and budding entrepreneurs through common service centres (CSC).

**(IV) An analysis may be done and shared if desired progress is not taking place.**

The department regularly evaluates the scheme's progress against set targets. As of June 14th, 2024, the department has reached 58.27% of its goal in terms of investment generated (project cost of eligible cases), based on the new corpus of 29110 cr. Launched in June 2020 amid the COVID-19 pandemic, the scheme has undergone significant streamlining. Aspiring animal husbandry entrepreneurs have received guidance to ensure smooth scheme operation. To assist applicants, model DPRs have been uploaded to the portal. The department has implemented numerous process simplifications to enhance the scheme's effectiveness and accessibility for participants.

**(V) The States with good performance and State with poor performance may also be mentioned (wherever applicable)**

Maharashtra has emerged as the top-performing state under the AHIDF scheme, showcasing exemplary results in agricultural development. Following closely behind are Karnataka, West Bengal, Tamil Nadu, and Uttar Pradesh, all of which have shown remarkable progress in implementing the scheme. Additionally, states like Gujarat and Odisha have demonstrated promising responses to the initiative.

Despite the success seen in certain regions, there is a concerted effort to enhance the participation of low-performing states such as the North-eastern states, Goa, and Himachal Pradesh. By encouraging more applications from these areas, we aim to create a more inclusive and comprehensive approach to agricultural growth nationwide.

**(6) Entrepreneurship Development Programme under National Livestock Mission:**

**(I) Objective of Scheme/Program -**

1. Employment generation through entrepreneurship development in small ruminant, poultry, and piggery sector & Fodder sector.
2. Increase in production of meat, egg, goat milk, wool, and fodder.
3. Encouraging establishment of fodder processing units to reduce the demand supply gap.

**(II)** **Physical and financial progress**

|  |  |  |
| --- | --- | --- |
| 1. | Total application received on the portal | 43210 |
| 2. | Total applications recommended by the States | 3031 |
| 3. | Total Applications Approved by Project Approval Committee (CEC) | 2679 |
| 4. | Total project cost for category wise applications marked approved by the Department (2679 Applications) | Rs. 1973.95 Cr.   * Entrepreneurial activities in feed and fodder (96 number) (Rs. 89.88 cr.) * Establishment of Entrepreneur for breed Development in small ruminant sector (sheep & goat Farming) (2151 number) (Rs. 1629.89 cr.) * Establishment of entrepreneurship for breed development of Rural Poultry (168 number) (Rs. 90.88 cr.) * Promotion of Piggery Entrepreneur (264 numbers) (Rs. 163.30 cr.) |
| 5. | Total Loan amount for category wise applications marked approved by the Department (2679 Applications) | Rs. 741.69 cr.   * Entrepreneurial activities in feed and fodder (96 numbers) (Rs. 32.89 cr.) * Establishment of Entrepreneur for breed Development in small ruminant sector (sheep & goat Farming) (2151 numbers) (Rs. 612.87 Cr.) * Establishment of entrepreneurship for breed development of Rural Poultry (168 numbers) (Rs. 34.89 Cr.) * Promotion of Piggery Entrepreneur (264 numbers) (Rs. 61.04 cr.) |
| 6. | Total Recommended Subsidy amount for category wise applications marked approved by the Department (2679 Applications) | Rs. 909.20 crores   * Entrepreneurial activities in feed and fodder (96 numbers) (Rs. 39.62 cr.) * Establishment of Entrepreneur for breed Development in small ruminant sector (sheep & goat Farming) (2151 numbers) (Rs. 764.75 cr.) * Establishment of entrepreneurship for breed development of Rural Poultry (168 numbers) (Rs. 40.28 cr.) * Promotion of Piggery Entrepreneur (264 numbers) (Rs. 64.55 cr.) |
| 7. | Total subsidy released to SIDBI till date | Rs. 238.47 Crore |
| 8. | Total amount of subsidy released by SIDBI | Rs. 231.41 Crore |

**(III) Efforts made for handholding/creating awareness about programs / process simplification etc. –**

* A four-day field visit to Telangana from September 25th to 28th, 2024 was done which aims to inspect the breeding farm and monitor the progress of projects approved under the NLM EDP scheme and to create awareness among farmers.
* Successfully conducted a meeting with the bankers under the chairmanship of SLBC convener, Telangana on 25th Sept, 2024, with the agenda to address branch-level pendency and to inform branches about the scheme designed to benefit farmers and applicants seeking subsidy support from the NLM EDP program.
* A Regional Review Meeting was conducted on September 12, 2024, followed by a Monsoon Meeting on September 13, 2024, in Bhubaneswar. The purpose of these meetings was to assess the progress of the scheme, address challenges and issues, review pending matters at the state level, and discuss potential opportunities.

**(IV) An analysis may be done and shared if desired progress is not taking place. –**

Till date total 43210 applications are received through the portal from various states and 1146 beneficiaries has received 1st installment of subsidy and 44 beneficiaries received 2nd installment of subsidy amounting to total Rs.231.41 Crores.

**(V) The States with good performance and State with poor performance may also be mentioned (wherever applicable).**

1. The State of Karnataka, Madhya Pradesh, Telangana, Andhra Pradesh and Maharashtra has recommended maximum number of applications.
2. No applications have been recommended by the states of Jharkhand, Meghalaya and UTs.
3. A meeting was conducted with all the state nodal officers to discuss the current status, challenges and ways to improve the present scenario of the NLM-EDP scheme on October 15th, 2024.

**(7) Livestock Health and Disease Control Programme (LHDCP)**

1. **Objective of the scheme / Programme** - Department of Animal Husbandry and Dairying (DAHD) is implementing a Central Sector Scheme, Livestock Health and Disease Control Programme (LHDCP). The scheme subsumes both the erstwhile Livestock Health and Disease Control Programme (LHDC) scheme and National Animal Disease Control Programme (NADCP). The aim of the programme is to reduce risk to animal health by prophylactic vaccination against diseases of animals, capacity building of Veterinary services, disease surveillance and strengthening veterinary infrastructure. The major activities supported are: Critical Animal Disease Control Programme (CADCP) for eradication and control of two major diseases namely *Peste des Petits Ruminants* (PPR) and classical swine fever (CSF); establishment and strengthening of mobile veterinary units (ESVHD); and Assistance to States for control of other economically important, exotic, emergent and zoonotic animal diseases (ASCAD).

Further, under NADCP, it is aimed to vaccinate all eligible susceptible livestock against Foot and Mouth Disease (FMD) biannually and all female bovine calves of 6-8 months’ age annually against Brucellosis to control of FMD and Brucellosis by 2025 with vaccination and eventual eradication of FMD by 2030.

1. **Achievements in terms of physical and financial progress:**
2. **Physical Progress under LHDC**
3. **MVU Related Activities**

**Status of Sanction so far for MVUs**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1. **Non- Recurring Funds** | | | | | |
| **Phase** | **No. of MVUs Sanctions** | **Funds Released** | | **Status** | |
| Phase -1 | 2,980 | 476.80 Cr. | | Funds Released to 22 States/UTs on 30.09.2021 | |
| Phase -2 | 551 | 76.61 Cr. | | Funds Released to 7 States/UTs on 29.11.2021 | |
| Phase -3 | 801 | 128.16 Cr. | | Funds Released to 4 States/UTs on 22.12.2021 | |
| Phase-4 | 8 | 1.28 Cr. | | Fund Released to the UTs of Andaman and Nicobar and Puducherry during FY 2022-23. | |
| TOTAL | **4,340** | **682.85 Cr.** | |  | |
| 1. **Recurring Funds** | | | | | |
| **Year** | | | **Funds Released** | | **No of States** |
| 2022-23 | | | 33.07 Cr. | | 7 States |
| 2023-24 | | | 184.87 Cr. | | 23 States |
| 2024-25 | | | 108.44 Cr. | | 20 States |

 Total 4016 no of MVUs are operational in 28 States.

* 1. **ASCAD**

**Financial Progress of ASCAD:**

|  |  |
| --- | --- |
| **Year** | **Funds Released** |
| 2019 – 2020 | 89.92 Cr. |
| 2020 – 2021 | 206.76 Cr. |
| 2021 – 2022 | 135.32 Cr. |
| 2022 – 2023 | 70.33 Cr. |
| 2023 - 2024 | 204.01 Cr. |
| 2024-2025 | 56.60 Cr. |

* + 1. **Status of LSD**

During 2024, LSD was reported in 11 states. Presently, there is no active cases under Lumpy Skin Disease. Total 5,57,90,780 animals have been vaccinated during 2024 and the vaccination is underway.

\* Above given information is as on 28.10.2024

* + - Funds have been provided to affected States for undertaking trainings, awareness campaigns and vaccination under ASCAD as per the demand. States are also advised the possibility to utilize the emergency funds of the state/district for control operations.
    - During the fiscal year 2023-24, a total amount of Rs. 63.51 Crore has been sanctioned to 27 States for 13.18 Crore doses of goat pox vaccine along with its vaccination costs. The total released against this allocation is Rs. 29.92 Crore.
    - A DO Letter has been issued for the fiscal year 2024-25 directing 25 states to implement the vaccination drive against LSD.

1. **Physical Progress under NADCP component of LHDCP**
2. **NADCP- FMD**

* DAHD has supplied total 25.05 crore FMD vaccine doses to 35 States and UTs for completion of round III FMD vaccination. Among which 24.23 Crore vaccination has been reported by State.
* Till date 25.71 crore vaccine doses have been supplied to 35 States and UTs for FMD vaccination round IV. Among which 21.56 Crore vaccination has been recorded till date.
* Till date total 18.49 crore (Including Haryana) vaccine doses have been supplied to 24 States and UTs for FMD round V. Among which 5.63 Crore vaccination done so far.
* Till date total 2.47 crore (Including Haryana) vaccine doses have been supplied to 2 states State for FMD round VI. . Among which 0.86 Crore vaccination done so far.
  1. **NADCP-Brucellosis**

**Summary of progress on vaccination against Brucellosis**

* + - Total Vaccines Supplied to States: 5.43 Crore
    - Total 4.24 Crore Brucellosis vaccination done so far.
    1. **PPR – EP**

**Summary of progress on vaccination against PPR – EP:**

* + - Vaccines Supplied for Round 1: 18.67 Crore doses to 31 States and UTs. Total 15.22 Crore PPR vaccination done so far.
    - Vaccines Supplied for Round 2: 13.18 Crore doses to 21 States. Total 2.22 Crores PPR vaccination done so far.
    - Cumulative total 17.44 Crore vaccination done so far in both rounds.
    1. **CSF – CP**

**Summary of progress on vaccination against CSF – CP:**

* + - Vaccines Supplied for Round 1: 69.60 Lakh doses to 28 States and UTs. Total 49.05 Lakh CSF vaccination done so far.
    - Vaccines Supplied for Round 2: 47.78 Lakh doses to 18 States. Total 10.86 Lakh CSF vaccination done so far.
    - Cumulative total 59.91 Lakh vaccination done so far in both rounds.

**Mobile Veterinary Units (MVUs):** The Department has provided funds for MVUs to the 33 States/UTs with the aim to provide veterinary services at the farmers' doorsteps. The farmers need not to bring animals from far, instead on call the veterinarians will visit the farmers. This may bring a revolution of Veterinary Services Pan India. MVUs out of which Total 4016 Nos. of MVUs are operational in 28 states.

**The States with good performance and State with poor performance may also be mentioned (wherever applicable):**

In the ongoing FMD round IV vaccination is completed in 24 States/UTs, i.e., Karnataka, Kerala, Tamil Nadu, Chandigarh, Goa, Andhra Pradesh, Delhi, Gujarat, Maharashtra, Jammu and Kashmir, Uttarakhand, Ladakh, Lakshadweep, Telangana, Odisha, Himachal Pradesh, Puducherry, Tripura, Andaman & Nicobar Islands, West Bengal, Uttar Pradesh, Madhya Pradesh, Haryana and Punjab and going on in 7 States/UTs**,** i.e., Assam, Chhattisgarh, Jharkhand, Manipur, Nagaland, Sikkim, and Rajasthan

In the ongoing FMD round V, vaccination completed in Karnataka, Andhra Pradesh, Haryana, Goa & Tamil Nadu and ongoing in Maharashtra, Kerala, Delhi, Puducherry, Telangana, Punjab and Uttarakhand.

-xxx-